## Sheet1
S.No. | Date | Sub Tasks | Status | Constraints
1 | 2013-12-16 | Impact analysis | done
|  | Current code analysis | done
|  | Rough design of the implementation | done
|  | Inclusion of service end point url in db | done
|  | web.xml and bean changes to expose the service | done
|  | Hessian Service, helper methods to return the task summary info from Payments by interacting with coverage manager service | done
|  | Hessian call in task summary to get the task summary info | done
|  | Integration of service call to the service exposed | Yet to be done | Facing lap top issues for the past four days due to which could not make enough progress
|  | New laptop which was got seemed to be faulty again, hence replacing with desktop | done
| 2013-12-17 | Configuring Task summary locally with the new desktop | done
| 2013-12-18 | Integration of service call to the service exposed | In progress | Was not able to resolve the issue and mailed to praveen
| 2013-12-19 | Integration of service call to the service exposed | done
|  | getting active work items from payments for task summary | done
|  | Adding the work items to task summary | in progress | development done, TaskSummaryInfo object returning null, Hence trying to fix the issue
|  | Testing the application locally | in progress
|  | Checking in code in Payments and Task summary | Mostly done, final part yet to be done
|  | Unit testing of the application in dev box | Yet to be done